## Sheet1
TASK TITLE | PHASE THREE
| WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
| M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Decide on program structure | bar: WEEK 1 M to WEEK 1 F
Optimize Brute Force method | bar: WEEK 1 W to WEEK 2 T
Write other lower-bound method | bar: WEEK 1 W to WEEK 2 T
Write the report | bar: WEEK 1 W to WEEK 3 W
Prepare for the presentation | bar: WEEK 2 R to WEEK 3 R